## Projects_Programmes
COUNTY GOVERNMENT OF MARSABIT
IMPLEMENTED PROJECTS AND PROGRAMMES DATA TEMPLATE
Department Name |  | AGRICULTURE, LIVESTOCK AND FISHERIES DEVELOPMENT | [7 empty] | CERTIFICATION
Directorate / Unit | [9 empty] | Prepared by | Designation | Signature | Date
CEC Member |  | ADAN KANANO | [7 empty] | DAVID | ADA |  | 2026-06-02
Chief Officer |  | ORGE G BAJJI
Reporting Officer |  | DAVID GITIRA | [7 empty] | Approved by | Designation | Signature | Date
Reporting Period |  | 2013 - 2026 | [7 empty] | WATO | CDA | Signed | 2026-06-02
Date of Submission
PROJECT 2017/2018 LANDS, ENERGY AND URBAN DEVELOPMENT
No. | Project / Programme Name | Sub-County | Ward | Location / Site | Objective | Implementation Period (FY) | Budget Allocated (KES) | Funding Source (County/Partnership) | Status (Complete/ Incomplete/Not Started) | % Completion | Key Achievements / Outputs | Beneficiaries (No.) | Evidence Available (Photos/videos)
2013- 2025
1 | Biogas construction moyale /marsabit | moyale/ marsabit | moyale marsabit | moyale marsabit |  | 2013-14 | 3600000 | county | complete | 100% |  | '
2 | Dirdima water pan | moyale | golbo | dabel |  | 2013-14 | 5459720 | county | complete
3 | Green house walda secondary schoo land golole youth -sololo | moyale | sololo/walda | sololo/walda |  | 2013-2014 | 1000000 | county | complete | 100%
4 | kinisa water pan | moyale | golbo | kinisa |  | 2013-2014 | 4480000 | county | complete | 100%
5 | Moyale beekeeping projects | Moyale | moyale | moyale |  | 2013-2014 | 1208000 | county | complete | 100%
6 | Dbu loni iiiwateer pan | North horr | Huri hills | huri hills |  | 2013-2014 | 5999980 | county | complete | 100%
7 | Maikon agilrs high school | North horr | maikona | maikona |  | 2013-2014 | 487000 | county | complete | 100%
8 | Gree n house drgodano memorial school | North horr | maikona | maikona |  | 2013-2014 | 487000 | county | complete | 100%
9 | green house | laisamis | logologo | logologo |  | 2013-2014 | 480000 | county | complete | 100%
10 | Badassa water pan | saku | sagante | badassa |  | 2013-2014 | 5293400 | county | complete | 100%
11 | Naibuga water pan | saku | karare | karare |  | 2013-2014 | 4451242 | county | complete | 100%
12 | Weeds control equipment | Marsabit | marsabit | county wide |  | 2013-2014 | 440000
13 | purchase of moto bike | marsabit | Mardsbit | county wide |  | 2013-2014 | 3393696
14 | Moyale slaughter house | moyale | moyale | moyale |  | 2013-14 | 3154324 | county | complete | 100%
15 | Auto boat engine | north horr | illeret | illeret |  | 2013-14 | 5200000 | county | complete | 100%
16 | fishing gears | North horr | illeret | illeret |  | 2013-14 | 990000 | county | complete | 100%
17 | Cold storage | north horr | illeret | illeret |  | 2013-14 | 5649838 | county | complete | 100%
18 | fish cold storage facilities | laisamis | loiyangalani | loiyangani |  | 2013-14 | 4599400 | county | complete | 100%
19 | Slaughter house | laisamis | laisamis | laisamis |  | 2013-14 | 5000000 | county | complete | 100%
20 | Slaughter house | Saku | saku | saku |  | 2013-14 | 5385004 | county | complete | 100%
21 | completion and/or renovation slughter house slabs | Moyale | Moyale | moyale |  | 2014-15 | 3500000 |  |  | 100%
22 | Suppy of farm tractors | Marsabit | Marsabit | county wide |  | 2014-15 | 13000000 |  | complete | 100%
23 | Establishing of seed bulking center | moyale | Moyale | moyale |  | 2014-15 | 4000000 |  | complete | 100%
24 | Scaling up of existing food production under Irrigation farming | North horr | south horr | south horr |  | 2014-15 | 6000000 |  | complete | 100%
25 | pioloting on alternative Bio energ productionfrom slaughter house effluents. | Moyale | moyale | moyale |  | 2014-15 | 1800000 | county | complete | 100%
26 | pioloting on alternative Bio energ productionfrom slaughter house effluents. | saku | marsabit | saku |  | 2014-15 | 1800000 | county | complete | 100%
27 | construction of fish cold storage facilities | north horr | illeret | illeret |  | 2014-15 | 5600000 | county
28 | construction of fish cold storage facilities | Laisamis | loiyangalani | loiyangani |  | 2014-15 | 4600000 | county | complete | 100%
29 | purchase of fibre glass boat &engine | north horr | ILLERET | illeret |  | 2014-15 | 2600000 | county | complete | 100%
30 | purchase of fibre glass boat &engine | Laisamis | loiyangalani | moyale |  | 2014-15 | 7305400 | county | complete | 100%
31 | Supply of fishing gears | north horr | illeret | MOITE |  | 2014-15 | 8000000 | county | complete | 100%
32 | installation of equiping fish cold storage facilities | North horr | illeret | illeret |  | 2014-2015 | 5800000 | county
33 | equiping& establing( 10)veterinary points with coldchain systems solar fridges deepfreezers | laisamis | loiyangani | loiyangani |  | 2014-15 | 5600000 | county | complete | 100%
34 | equiping& establing( 10)veterinary points with coldchain systems solar fridges deepfreezers | laisamis | laisamis | kargi,oltorot,korr,merille |  | 2014-15 | 2500000 | county | complete | 100%
35 | establishing &equiping (10)veterinary checkpoints with cold chain systems (solr fridges ,deep freezers | moyale | moyale | moyale |  | 2014-15 | 500000 | county | complete | 100%
36 | establishing &equiping (10)veterinary checkpoints with cold chain systems (solr fridges ,deep freezers | saku | saku | shurr |  | 2014-15 | 500000 | county | complete | 100%
37 | establishing &equiping (10)veterinary checkpoints with cold chain systems (solr fridges ,deep freezers | moyale | moyale | moyale |  | 2014-15 | 500000 | county | complete | 100%
38 | establishing &equiping (10)veterinary checkpoints with cold chain systems (solr fridges ,deep freezers | north horr | dukan | burgabo ,forole,dukana ,illeret |  | 2014-15 | 2000000 | county | complete | 100%
39 | Renovation of staff quarter and labaratory | saku | shurr | shurr |  | 2014-15 | 5000000 | county | complete | 100%
40 | mobile veterinary clinic (Pick Up Van) | SAKU | SAKU | SAKU |  | 2014-15 | 8000000 | county | complete | 100%
41 | construction of modern Abbortoir | SAKU | SEGEL |  |  | 2014-15 | 30000000 | county | not complete
42 | Construction of forole livestock Stalls | north horr | forole | forole |  |  | 500000 | county | complete | 100%
43 | Construction of water pan at ALIA | Laisamis | laisamis | Alia |  |  | 5000000 | county | complete | 100%
44 | COnstruction of water pan at NATADE | laisamis | laisamis | natade |  | 2015-2016 | 5000000 | county | complete | 100%
45 | Consruction of ubderground water tank | north horr | turbi | bubisa |  | 2015-2016 | 2000000 | county | complete | 100%
46 | installation of greenhouse complete with drip irrigation | saku | cental | dakabaricha |  | 2015-2016 | 1500000 | county | complete | 100%
47 | purchase of farm tractors | Marsbit | marsabit | county wide |  | 2015-2016 | 8000000 | county | complete | 100%
48 | purchase/suply of&installation of irrigaation system & equipment | laisamis | laismis | nkororoi |  | 2015-2016 | 8000000 | county | complete | 100%
49 | installation of shade nets and green houses | laisamis | laisamis | lontolio /koya ulauli |  | 2015-2016 | 1500000 | county | complete | 100%
50 | purchase &installation of shade nets /greenhouse & tank | Laisamis | Laisamis | Laisamis /Nairibi |  | 2015-2016 | 1000000 | county | complete | 100%
51 | Construction of cereals stores | Saku | karare | leyai |  | 2015-2016 | 1723843 | county | complete | 100%
52 | consultancy solr drying | marsabit | marsabit | HQ |  | 2015-206 | 1500000 | county | complete | 100%
53 | construction of loading lump & crush | north horr | turbi | tigo |  | 2015-2016 | 3500000 | county | complete | 100%
54 | construction of slaughter house | northhorr | bubisa | bubisa |  | 2015-2016 | 2500000 | county | complete | 100%
55 | proposed erection and completion of slaughter | moyale | moyale | moyale |  | 2015-2016 | 6000000 | county | complete | 100%
56 | proposed erection and completion of slaughter | north horr | dukana | dukana |  | 2015-2016 | 3000000 | county | complete | 100%
57 | Refurbiment of slaughter house | laisamis | logologo | logologo |  | 2015-16 | 2000000 | county | complete | 100%
58 | Milk equipment and reagent | saku | shurr | shurr |  | 2015-16 | 999412 | county | complete | 100%
59 | construction of livestock market | Laisamis | logologo | logologo |  | 2015-16 | 3500000 | county | complete | 100%
60 | construction of modern ABBORTOIR | noth horr | SEGEL | SEGEL |  | 2015-16 | 80000000 | county | NOT complete
61 | Supply cold storage fridges for traders | saku | saku | saku |  | 2015-16 | 1865000 | county | complete | 100%
62 | mobile vet clinic | noth horr | ileret | telesgaye |  | 2015-16 | 1020000 | county | complete | 100%
63 | Mineral urea blocks | saku | marsabit | saku |  | 2016-2017 | 797616 | county | complete | 100%
64 | Supply of labaratory equipment | saku | marsabit | saku |  | 2016-2017 | 830402 | county | complete | 100%
65 | Constuction of slaughter house | moyale | sololo | sololo ramata |  | 2016-2017 | 3434702 | county | complete | 100%
66 | Constuction of slaughter house | moyale | sololo | sololomakutano |  | 2016-2017 | 2499800 | county | complete | 100%
67 | Supply of veterinay drugs | saku | saku | countywide |  | 2016-2017 | 1069600 | county | complete | 100%
68 | purchase of resque boat | laisamis | loiyangalani | laisamia |  | 2016-2017 | 6000000 | county | complete | 100%
69 | Supply of fishing gears | noth horr | loiyangalani | loiyangalani |  | 2016-2017 | 960000 | county | complete | 100%
70 | Supply of cold storage | noth horr | loiyangalani | loiyangalani |  | 2016-2017 | 1200000 | county | complete | 100%
71 | Supply of veterinay drugs | saku | marsabit | countywide |  | 2016-2017 | 7606600 | county | complete | 100%
72 | supply of beekeeping equipment | saku | marsabit | countywide |  | 2016-2017 478900 | 478900 | county | complete | 100%
73 | Construction of crush and loading ramp | laismis | korr | korr |  | 2016-2017 478901 | 3495000 | county | complete | 100%
74 | Consruction &completion of dry fish stores and solar lighting | Noth horr | loiyangani | silicho |  | 2016-17 | 6000000 | county
75 | Erection and competion of slaughter house | Noth horr | Noth horr | Noth horr |  | 2016-17 | 6504735 |  | complete | 100%
76 | Erectin and competion of genset house supply and Installation of 20kva(phase3) | Noth horr | Loiyangalani | Loiyangalani |  | 2016-17 | 3039490 | county | complete | 100%
77 | installation of solar items fisheries office | saku | saku | HQ |  | 2016-17 | 298800 | county | complete | 100%
78 | Design spate irrigation | laisamis |  | kurungu |  | 2015-16 | 8000000 | county | complete | 100%
79 | Design spate irrigation | noth horr |  | Elgade |  | 2016-2017 | 13000000 | county | complete | 100%
80 | Suply of pusture seeds | saku /moyale |  | saku /moyale |  | 2016-2017 | 1100000 | county | complete | 100%
81 | Supply of tractor implements | marsabit | saku | countywide |  | 2016-2017 | 7606600 | county | complete | 100%
82 | Erection and completion of ATC | Moyale | golbo | misa |  | 2016-2017 | 4900000 | county | complete | 100%
83 | supply &delivery of certified seeds | Marsabit | marsabit | countywide |  | 2016-2017 | 1312800 | county | complete | 100%
84 | Supply /delivery of 10 improved borana bull cross breeds with local zebu approx 3yrs | Laisamis | south horr | mt kulal |  | 2016-2017 | 1980000 | county | complete | 100%
85 | Design & implementation of drip irrigation at Ririma | Kargi/South Horr | Ririma | Dukana |  | 2017/2018 | 5000000 | county | complete | 100%
86 | Design of spate irrigation for Kurungu in South Horr | Kargi/South Horr | Kurungu | Maikona |  | 2017/2018 | 8000000 | county | complete | 100%
87 | Micro -irrigation support at Walda | Uran | Walda | marasabit |  | 2017/2018 | 5000000 | county | complete | 100%
88 | Equiping Misa ATC | Golbo | Misa | laisamis town |  | 2017/2018 | 4000000 | county | complete | 100%
89 | Micro -irrigation support at Mado Adhi | Sololo | Mado Adhi | korr town |  | 2017/2018 | 5000000 | county | complete
90 | Design & implementation of spate irrigation for Elgadhe | Maikona | El Gadhe | sololo ramat |  | 2017/2018 | 10000000 | county | complete | 100%
91 | Design & implementation of spate irrigation at Jaldesa ,Kubi Qallo & Ilpus | Sagante/Jaldesa | Jaldesa/Kubi Qallo/Ilpus | butiye |  | 2017/2018 | 15000000 | county | complete | 100%
92 | Support to agricultural mechanisation Services | Moyale | Moyale | manyatta |  | 2017/2018 | 5000000 | county | complete | 100%
93 | Purchase of certified seeds - Agricultural Seeds | Cross-Cutting | Cross-Cutting | sololo makutano |  | 2017/2018 | 5000000 | county | complete | 100%
94 | Support to agricultural mechanisation Services & Purchase of one tractor | Cross-Cutting | Cross-Cutting | sagante |  | 2017/2018 | 15000000 | county | complete | 100%
95 | Twin latrine for Laisamis Vet office | Laisamis | Laisamis | Laisamis |  | 2017/2018 | 800000 | county | complete | 100%
96 | Construction of cattle crash, holding yard and loading ramp | Logologo | Midroc borehole | Midroc borehole |  | 2017/2018 | 4000000 | county | complete | 100%
97 | Cattle crush/Loading Ramp | Uran | Elebor | Elebor |  | 2017/2018 | 3000000 | county | complete | 100%
98 | Holding yard/Cattle Crush & Loading ramp | Obbu | Badan Rero | Badan Rero |  | 2017/2018 | 3000000 | county | complete | 100%
99 | Sololo Slaughter house Masonary tank and guttering - 50M3 | Sololo | Ramata | Ramata |  | 2017/2018 | 2000000 | county | complete | 100%
100 | Cattle Crash and holding yard (2) | Maikona | Hurri Hills | Hurri Hills |  | 2017/2018 | 4000000 | county | complete | 100%
101 | 50M3 Masonary Tanks and equipment and guttering - Dukana Slaughter | Dukana | Dukana | Dukana |  | 2017/2018 | 2000000 | county | complete | 100%
102 | Construction of livestock handling yard | Dukana | Dukana | Dukana |  | 2017/2018 | 2000000 | county | complete | 100%
103 | Soak pit/septic tank for disposal of blood and ruminal content | Dukana | Dukana | Dukana |  | 2017/2018 | 500000 | county | complete | 100%
104 | Construction of toilet ,purchase & installation of 10M3 plastic water tank at Bubisa slaughter house | Turbi | Bubisa | Bubisa |  | 2017/2018 | 1000000 | county | complete | 100%
105 | Construction of slaughter house,toilet &10M3 plastic water tank at Turbi | Turbi | Turbi | Turbi |  | 2017/2018 | 3000000 | county | complete | 100%
106 | Veterinary vaccines and Supplies | County wide | County wide | County wide |  | 2017/2018 | 20000000 | county | complete | 100%
107 | Cold room facility - Toilet & piping | Loiyangalani | Loiyangalani | Loiyangalani |  | 2017/2018 | 1500000 | county | complete | 100%
108 | Generator and Fencing of Fish cold storage facility | Illeret | Illeret | Illeret |  | 2017/2018 | 5000000 | county | complete | 100%
109 | Purchase of Rescue Boat | Loiyangalani | Loiyangalani | Loiyangalani |  | 2017/2018 | 10000000 | county | complete | 100%
110 | Supplies for production(fishing equipment, pasture seeds & bee keeping equipment | County wide | County wide | County wide |  | 2017/2018 | 6000000 | county | complete | 100%
111 | Construction of micro irigation store /office | Uran | walda | walda |  | 2018/2019 | 1000000 | county | complete | 100%
112 | Construction of community food store at Sabarei trading centre | Dukana | Sabarei | Sabarei |  | 2018/2019 | 1500000 | county | complete | 100%
113 | Piping of water to slaughter house | North Horr | Gas | Gas |  | 2018/2019 | 1000000 | county | complete | 100%
114 | Disilting and weeding of Hori Gudha | North Horr | North Horr | North Horr |  | 2018/2019 | 2440000 | county | complete | 100%
115 | supply of fodder seeds for buura irrigation | North Horr | Buura | Buura |  | 2018/2019 | 500000 | county | complete | 100%
116 | Drilling of borehole at Buura for irrigation | North Horr | Buura | Buura |  | 2018/2019 | 3000000 | county | complete | 100%
117 | Equipping of buura borehole with solar power,pump and overhead tank | North Horr | Buura | Buura |  | 2018/2019 | 3000000 | county | complete | 100%
118 | Clearing of prosopis (Alga Roba) at Burra | North Horr | Buura | Buura |  | 2018/2019 | 2000000 | county | complete | 100%
119 | Construction and furnishing of office block for KFW project at headqquarters | Marsabit | Marsabit | Marsabit |  | 2018/2019 | 5000000 | county | complete | 100%
120 | Purchase of hand tools and equipments for farmers | County wide | County wide | County wide |  | 2018/2019 | 6500000 | county | complete | 100%
121 | Development of Sagante Agricultural Mechanization Station(Fencing,gate) | Saku | Saku | Saku |  | 2018/2019 | 2000000 | county | complete | 100%
122 | Purchase of certified seeds - Agricultural Seeds | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2018/2019 | 8000000 | county | complete | 100%
123 | Construction of Agriculture office for KCSAP at Sagante | Sagante | Sagante | Sagante |  | 2018/2019 | 5000000 | county | complete | 100%
124 | Purchase of milling equiment | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2018/2019 | 2000000 | county | complete | 100%
125 | Purchase of puncture repair kits(hydraulic pumps*14) | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2018/2019 | 1500000 | county | complete | 100%
126 | Completion of slaughter | Loglogo | Loglogo centre | Loglogo centre |  | 2018/2019 | 2000000 | county | complete | 100%
127 | Construction of Slaughter house | Kargi | Kargi centre | Kargi centre |  | 2018/2019 | 2000000 | county | complete | 100%
128 | Construction of slaughter house | Kargi | South Horr | South Horr |  | 2018/2019 | 2000000 | county | complete | 100%
129 | Construction of Mettalic crush | Obbu | Ambalo | Ambalo |  | 2018/2019 | 1000000 | county | complete | 100%
130 | Construction metallic cattle crush | Sololo | Anona | Anona |  | 2018/2019 | 1500000 | county | complete | 100%
131 | Construction metallic cattle crush | Sololo | Sololo | Sololo |  | 2018/2019 | 1500000 | county | complete | 100%
132 | Construction of mettalic cattle crush | Uran | Lataka | Lataka |  | 2018/2019 | 2500000 | county | complete | 100%
133 | Construction of slaughter house | Maikona | Forole | Forole |  | 2018/2019 | 3200000 | county | complete | 100%
134 | Equipping of livestock market resort | Maikona | Forole | Forole |  | 2018/2019 | 500000 | county | complete | 100%
135 | Construction of Shallow wells and fitting with hand pump at Kalach Slaughter house | Maikona | Kalacha Slaughter | Kalacha Slaughter |  | 2018/2019 | 700000 | county | complete | 100%
136 | Construction of Pit latrine at Kalacha slaughter house | Maikona | Kalacha Slaughter | Kalacha Slaughter |  | 2018/2019 | 500000 | county | complete | 100%
137 | construction of slaughter House | Maikona | maikona | maikona |  | 2018/2019 | 2000000 | county | complete | 100%
138 | Cattle Crush,Holding yard,fencing and public toilet | Karare | Songa | Songa |  | 2018/2019 | 1000000 | county | complete | 100%
139 | New livestock market at Karare | Karare | Karare | Karare |  | 2018/2019 | 3000000 | county | complete | 100%
140 | Construction of mettalic cattle crush | Karare | kituruni | kituruni |  | 2018/2019 | 1500000 | county | complete | 100%
141 | Fencing of the livestock market | Karare | Karare | Karare |  | 2018/2019 | 1000000 | county | complete | 100%
142 | 2 Toilets and Water Tank | Karare | Karare | Karare |  | 2018/2019 | 1000000 | county | complete | 100%
143 | Veterinary vaccines and Supplies | County wide | County wide | County wide |  | 2018/2019 | 8000000 | county | complete | 100%
144 | Purchase of fishing gears and development of fish landing sites | North Horr | Charigollo | Charigollo |  | 2018/2019 | 3200000 | county | complete | 100%
145 | Beach management unit (BMU) seed money and capacity building | North Horr | Charigollo | Charigollo |  | 2018/2019 | 2300000 | county | complete | 100%
146 | Cold Chain Development | North Horr | Charigollo | Charigollo |  | 2018/2019 | 1500000 | county | complete | 100%
147 | Construction of Fish Factory at Loiyangalani | Loiyangalani | Loiyangalani | Loiyangalani |  | 2018/2019 | 7180000 | county | complete | 100%
148 | Construction of 5 fish processing slabs | Illeret | Illeret | Illeret |  | 2018/2019 | 1500000 | county | complete | 100%
149 | Repair ,Installation and improvement of Greenhouses | Laisamis/Merille | Nairibi |  |  | 2019/2020 | 1200000 | county | complete | 100%
150 | Agricultural Mechanization Services | County wide | County wide | County wide |  | 2019/2020 | 3200000 | county | complete | 100%
151 | Purchase of certified seeds - Agricultural Seeds | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2019/2020 | 4500000 | county | complete | 100%
152 | Metallic cattle crush with a loadin rump | Dukana | Dukana | Dukana |  | 2019/2020 | 1500000 | county | complete | 100%
153 | Purchase of vaccine and sera | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2019/2020 | 9000000 | county | complete | 100%
154 | fencing of fish factory area at Loiyangalani | Loiyangalani | Loiyangalani | Loiyangalani |  | 2019/2020 | 1400000 | county | complete | 100%
155 | Construction of retail shop at fish factory | Loiyangalani | Loiyangalani | Loiyangalani |  | 2019/2020 | 1600000 | county | complete | 100%
156 | Construction of guard house at fish factory | Loiyangalani | Loiyangalani | Loiyangalani |  | 2019/2020 | 1200000 | county | complete | 100%
157 | Purchase and delivery of cool boxes | illeret | illeret | illeret |  | 2019/2020 | 2000000 | county | complete | 100%
158 | Purchase and delivery weighing scale | Loiyangalani | Loiyangalani | Loiyangalani |  | 2019/2020 | 1600000 | county | complete | 100%
159 | Construction of food store | Sololo | Anona | Anona |  | 2020/2021 | 1500000 | county | complete | 100%
160 | Construction of community food store at Balesa Saru | Dukana | Balesa Saru | Balesa Saru |  | 2020/2021 | 1500000 | county | complete | 100%
161 | Agricultural Mechanization Services | County wide | County wide | County wide |  | 2020/2021 | 4200000 | county | complete | 100%
162 | Construction of Community food store | Dukana | Buluk | Buluk |  | 2020/2021 | 2000000 | county | complete | 100%
163 | Purchase of certified seeds - Agricultural Seeds | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2020/2021 | 4300135 | county | complete | 100%
164 | Clearing of Prospis at Ngurunit | Korr | Korr | Korr |  | 2020/2021 | 1000000 | county | complete | 100%
165 | Construction of modern slaughter house | Loyangalani | Loiyangalani Centre | Loiyangalani Centre |  | 2020/2021 | 3500000 | county | complete | 100%
166 | Fencing of Korr slaughter house | Korr | Korr | Korr |  | 2020/2021 | 1300000 | county | complete | 100%
167 | Fencing of Livestock market | Loglolgo | Loglolgo | Loglolgo |  | 2020/2021 | 1000000 | county | complete | 100%
168 | Purchase of Animal drugs | N/Horr | Across | Across |  | 2020/2021 | 1300000 | county | complete | 100%
169 | Procurement of livestock drugs | Dukana | Ward wide | Ward wide |  | 2020/2021 | 2000000 | county | complete | 100%
170 | Equipping of livestock service centre | Illeret | Illeret | Illeret |  | 2020/2021 | 2700000 | county | complete | 100%
171 | Completion of Maikona slaughter house | Maikona | Maikona | Maikona |  | 2020/2021 | 1000000 | county | complete | 100%
172 | Purchase of vaccine and sera | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2020/2021 | 5000000 | county | complete | 100%
173 | Purchase of wooden boat and nets | El-molo bay | El-molo bay | El-molo bay |  | 2020/2021 | 2000000 | county | complete | 100%
174 | Construction and equipping of fisheries office(3rooms) at Nyekomol with double pit latrine | Nyekomol | Nyekomol | Nyekomol |  | 2020/2021 | 6000000 | county | complete | 100%
175 | Purchase and delivery of fishing gears for 4 BMUs | Illeret | Illeret | Illeret |  | 2020/2021 | 5000000 | county | complete | 100%
176 | Purchase and delivery of cooler boxes | Illeret | Illeret | Illeret |  | 2020/2021 | 2000000 | county | complete | 100%
177 | Purchase and delivery of digital weighing scales | Illeret | Illeret | Illeret |  | 2020/2021 | 1500000 | county | complete | 100%
178 | Fish Factory Loiyangalani | Loiyangalani | Loiyangalani | Loiyangalani |  | 2020/2021 | 10000000 | county | complete | 100%
179 | Local purchase for tree seedling and fruit tree | Sagante/Jaldesa | Sagante/Jaldesa | Sagante/Jaldesa |  | 2021/2022 | 1400000 | county | complete | 100%
180 | Agricultural Mechanization Services | County wide | County wide | County wide |  | 2021/2022 | 3000000 | county | complete | 100%
181 | Purchase of certified seeds - Agricultural Seeds | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2021/2022 | 2000000 | county | complete | 100%
182 | Support to Mansile Agricultural Youth group Olla Qanchora Guyo | Heilu/Manyatta | Mansile | Mansile |  | 2021/2022 | 1500000 | county | complete | 100%
183 | Purchase of vaccine and sera | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2021/2022 | 2000000 | county | complete | 100%
184 | Completion of Fish Factory Loiyangalani | Loiyangalani | loiyangalani | loiyangalani |  | 2021/2022 | 12000000 | county | complete | 100%
185 | Supply and delivery of fishing nets | loiyanagalani | loiyangalani | loiyangalani |  | 2021/2022 | 3000000 | county | complete | 100%
186 | Construction of Double pit latrine at 4 Fish landing sites | Illeret | Illeret | Illeret |  | 2021/2022 | 3000000 | county | complete | 100%
187 | Bura irrigation tank installation, fencing and piping of water | North hor | North hor | North hor |  | 2022/2023 | 4000000 | county | complete | 100%
188 | Purchase of vaccine and sera | Cross cutting | Cross cutting | Cross cutting |  | 2022/2023 | 2000000 | county | complete | 100%
189 | Agricultural Mechanization Services | Cross cutting | Cross cutting | Cross cutting |  | 2022/2023 | 3000000 | county | complete | 100%
190 | Purchase of certified seeds - Agricultural Seeds | Cross cutting | Cross cutting | Cross cutting |  | 2022/2023 | 2000000 | county | complete | 100%
191 | Agricultural Mechanization Services | County wide | County wide | County wide |  | 2023/2024 | 10000000 | county | complete | 100%
192 | Purchase of certified seeds - Agricultural Seeds | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2023/2024 | 10000000 | county | complete | 100%
193 | Purchase of vaccine and sera | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2023/2024 | 15000000 | county | complete | 100%
194 | Restocking programme | Butiye | Butiye | Butiye |  | 2023/2024 | 4000000 | county | complete | 100%
195 | Restocking programme | Butiye | Somare | Somare |  | 2023/2024 | 3000000 | county | complete | 100%
196 | Restocking programme | Butiye | Bori | Bori |  | 2023/2024 | 3000000 | county | complete | 100%
197 | Construction of new slaughter house,water piping & renovation of water Tank | Dukana | Dukana | Dukana |  | 2023/2024 | 3000000 | county | complete | 100%
198 | Maintenance of Plant, Machinery and equipment | County wide | County wide | County wide |  | 2024-2025 | 8000000 | county | complete | 100%
199 | Purchase of certified seeds | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2024-2025 | 10000000 | county | complete | 100%
200 | Veterinarian Supplies Materials | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2024-2025 | 10000000 | county | complete | 100%
201 | Purchase of laboratory equipment and supplies | Cross-Cutting | Cross-Cutting | Cross-Cutting |  | 2024-2025 | 1000000 | county | complete | 100%
202 | Range land rehabilitation | Sagante/Jaldesa | Ward wide | Ward wide |  | 2024-2025 | 4900000 | county | complete | 100%
203 | Restocking of livestock at Leyai Sublocation (Cows) | Karare | Leyai | Leyai |  | 2024-2025 | 4000000 | county | complete | 100%
204 | Restocking programme ward wide. | Dukana | Dukana | Dukana |  | 2024-2025 | 14000000 | county | complete | 100%
205 | Restocking of Manyatta Horonder/Mude | Turbi | Horonder | Horonder |  | 2024-2025 | 2000000 | county | complete | 100%
206 | Restocking of Kambi Nyoka, Yaa Odola and Demo | Turbi | Kambi Nyoka, Yaa Odola and Demo | Kambi Nyoka, Yaa Odola and Demo |  | 2024-2025 | 2000000 | county | complete | 100%
207 | Restocking at Tigo, Burgabo, Yaa Galbo and Kukufami | Turbi | Tigo, Burgabo, Yaa Galbo and Kukufami | Tigo, Burgabo, Yaa Galbo and Kukufami |  | 2024-2025 | 4000000 | county | complete | 100%
208 | Fencing of Maikona slaughter house(1.5M). | Maikona | Maikona | Maikona |  | 2024-2025 | 1500000 | county | complete | 100%
209 | Restocking (Purchase of Goats for Yaa Gara, Burarat,Forole) | Maikona | Yaa Gara, Burarat,Forole | Yaa Gara, Burarat,Forole |  | 2024-2025 | 5000000 | county | complete | 100%
210 | Resilience programme for the Whole ward | Loglogo | wardwide | wardwide |  | 2024-2025 | 4900000 | county | complete | 100%
891607439
Notes

## Impact_Outcomes
No. | Project / Programme | Observed Impact on Community | Social / Economic Benefits | Sustainability Measures
1 | Support to agricultural mechanization services(Repair and maintaince of Agricultral tractors, ploughing) | Improved utilization of agricultural tractors leading to timely land preparation and expansion on area under cultivation of crops | Household incomes and food security improved due to higher farm productivity. | Sustainability is ensured through cost-sharing mechanisms, routine tractor maintenance, capacity building of farmers and enhanced community ownership of the programs.
2 | Support with drought recovery Certified crop seeds | Farmers experienced improved crop establishment, uniform growth, and increased confidence in farming due to access to quality and reliable planting materials. | Use of certified seeds led to higher yields, improved food security, increased household incomes, and reduced risk of crop failure, thereby strengthening local economies. | Sustainability is promoted through farmer sensitization on seed reuse limitations, linkages with accredited seed suppliers, promotion of seed multiplication groups, and continuous extension support.
3 | Construction and Completion of Fish factory in loiyangalani | Improved fish handling conditions hence enhanced hygiene during processing and storage | Household incomes and food security improved due to enhanced storage and preservation facilities. | Strengthening of BMUs for sustained market supply
4 | Restocking | Following the severe drought, the county implemented a livestock restocking program targeting the most affected households to restore lost herds and rebuild livelihoods in the year 2024 and 2025. | Restocking contributed to renewed income generation from milk and livestock sales, reduced dependency on relief assistance, and stimulated local livestock markets and related services | Provision of drought-resilient livestock breeds, linkage to animal health services, pasture and water management practices, and community-based livestock management systems.
5 | Vaccination programmes | Improved strong community participation in cattle vaccination campaigns, leading to timely improved control of livestock diseases. | Healthier livestock, reduced disease-related losses, lower treatment costs, and increased employment opportunities along the livestock value chain. | Sustainability is ensured through cost-sharing mechanisms, continuous vaccination schedules, capacity building of animal health workers.

## Cross_Cutting_Issues
No | Project / Programme | Gender & Youth Inclusion | Climate & Environment | PWD Inclusion | Peace & Social Cohesion
1 | Agricultural Mechanization Services | Youth and women are given priority as some of them are vulnerable | Establishment of agroforestry tree nurseries is a component for environmental conservetion | The vulnerable households are given first priority especially widows and child headed households | Enhanced food security and improved household incomes
2 | Vaccination | Youth and women are given priority as some of them are vulnerable | Safe disposal of the finished drug containers is observed | The vulnerable households are given first priority especially widows and child headed households
3 | Fish Factory | Youth and women are given priority as some of them are vulnerable | Proper waste disposal measures are given a lot of emphasis | Measures are pit in place to allow access to the premises by the people with disabilities.
4 | Restocking | Youth and women are given priority as some of them are vulnerable | Rangeland ecosystem restoration is a key area communities are sensitized on | The vulnerable households are given first priority especially widows and child headed households | Enhanced food security and improved household incomes
5 | Drought recovery Certified crop seeds | Youth and women are given priority as some of them are vulnerable | Soil and water conservation measures are put in place | The vulnerable households are given first priority especially widows and child headed households | Enhanced food security and improved household incomes

## Challenges_Lessons
No | Project / Programme | Key Challenges | Mitigation Measures | Lessons Learnt
1 | Agricultural Mechanization Services | Delayed tractor repairs due to delay in budgetary flow from the National treasury and inadequate fuel for ploughing | Tractor repairs should be done early to allow for more land to be ploughed | Early planning is required to achieve the planned targets
2 | Vaccination | Coverage of all the livestock has been a challenge due to budgetary constraints | More resources shold be mobilized for full coverage during vaccination
3 | Fish Factory | Surging of Lake Turkana has marooned the fishing infrastructure in Loiyangalani and Illeret | Hydrological surveys should be thoroughly done to keep key infrastructure from being marooned by the lake in future. | Following hydrological surveys before setting up any infrastructure in Illeret and Loiyangalani is key for all future projects
4 | Restocking | Due to budgetary constraints all vulnerable households were not covered | More resources shold be mobilized to allow more beneficiaries to be covered