## Projects_Programmes
COUNTY GOVERNMENT OF MARSABIT
IMPLEMENTED PROJECTS AND PROGRAMMES DATA
Department Name |  | ROADS AND TRANSPORT | [7 empty] | CERTIFICATION
Directorate / Unit |  | ROADS | [7 empty] | Prepared by | Designation | Signature | Date
CEC Member |  | GUYO GURACHA | [7 empty] | BORU SANTE | ROADS ENGINEER | Signed | 2026-02-05
Chief Officer |  | DR.HITLER RIKOI
Reporting Officer |  | BORU SANTE | [7 empty] | Approved by | Designation | Signature | Date
Reporting Period |  | 2017 - 2026 | [7 empty] | DR.HITLER RIKOI | CHIEF OFFICER | Signed | 2026-02-05
Date of Submission |  | 05/02/026
No. | Programme Name | Sub-County | Ward | Location / Site | Objective | Implementation Period (FY) | Budget Allocated (KES) | Funding Source (County/Partnership) | Status (Complete/ Incomplete/Not Started) | % Completion | Key Achievements / Outputs | Beneficiaries (No.) | Evidence Available (Photos/videos)
1 | County Road Routine Maintenance Programme (Grading Works) | saku,Laisamis,Moyale,North-Horr | All 20 Wards | County Wide | To improve and maintain motorable conditions of existing county roads through regular grading | 2017/18-2024/25 | 504632000 | County/KRB | Completed | 100 | Increased access to essential service,Reduced time travel,reduced vehicle operation cost through grading a total of 2078Kms of county road network | 380000
2 | County Road Improvement Programme (Gravelling Works) | saku,Laisamis,Moyale,North-Horr | All 20 Wards | County Wide | To strengthen road surfaces and improve durability of county roads by providing gravel wearing courses, thereby enhancing road performance, safety, and accessibility, especially in rural and high-traffic areas. | 2017/18-2024/25 | 877620000 | County/KRB | Completed | 100 | Increased access to essential service,Reduced time travel,reduced vehicle operation cost through gravelling a total of 690Kms of county road network | 250000
3 | County Road Upgrading and Surfacing Programme (Bituminous/Tarmac Roads) | saku,Moyale | Butiye ,Central | County Wide | To upgrade selected county roads to bituminous standards in order to improve long-term serviceability, promote economic growth, enhance road safety, and reduce maintenance costs. | 2017/18-2024/25 | 616000000 | County | Completed | 100 | Increased access to essential service,Reduced time travel,reduced vehicle operation cost through tarmacking a total of 7.4Kms of Urban road | 120000
4 | County Road Network Expansion Programme (New Road Openings) | saku,Laisamis,Moyale,North-Horr | 12Wards | 12 wards | To expand the county road network by opening new access roads that connect underserved areas, improve mobility, support service delivery, and unlock socio-economic development. | 2017/18-2024/25 | 131640000 | County/KRB | Completed | 100 | Increased access to essential service,Reduced time travel,reduced vehicle operation cost through opening a total of 585Km of Rural access road | 180000
5 | County Road Drainage and Crossings Infrastructure Programme (Covering slabs, drifts, culverts, and related structures) | saku,Laisamis,Moyale,North-Horr | All 20 Wards | County Wide | To provide and improve road drainage and crossing structures to ensure safe passage, minimize flood damage, protect road assets, and enhance year-round accessibility. | 2017/18-2024/25 | 65820000 | County/KRB | Completed | 100 | Improved drainages by constructing total 4.88 Km of drainage structures | 330000
6 | County Pedestrian Access - Footbridge Development Programme | saku,,Moyale | Golbo,Butiye,Township,Central | Golbo,Butiye,Township,Central | To enhance safe pedestrian mobility by constructing footbridges and pedestrian crossings, particularly in flood-prone and high-risk areas, thereby improving access to schools, health facilities, markets, and other essential services. | 2017/18-2024/25 | 45000000 | County | Completed | 100 | Improved pedestrian safety in flood-prone and high-traffic areas Enhanced access to schools, health facilities, markets, and water points through construction of 6No. footbridges | 50000

## Impact_Outcomes
No. | Programme | Observed Impact on Community | Social / Economic Benefits | Sustainability Measures
1 | County Road Routine Maintenance Programme (Grading Works) | Improved road passability, reduced isolation of rural communities, and easier movement during dry seasons | Reduced transport costs, improved access to markets, schools and health facilities, enhanced mobility for pastoral and trading activities | Regular grading schedules, routine inspection, use of county equipment and local labour for maintenance
2 | County Road Improvement Programme (Gravelling Works) | Improved road surface condition, reduced dust and erosion, enhanced all-weather access | Increased trade efficiency, reduced vehicle maintenance costs, improved safety and travel reliability | Proper drainage provision, quality gravel material selection, periodic re-gravelling and maintenance
3 | County Road Upgrading and Surfacing Programme (Bituminous/Tarmac Roads) | Improved road durability, smoother travel, enhanced connectivity in urban and high-traffic corridors | Stimulated economic growth, reduced travel time, increased investment, improved road safety | Durable pavement design, scheduled routine and periodic maintenance, enforcement of axle load limits
4 | County Road Network Expansion Programme (New Road Openings) | Improved access to previously unreachable areas, enhanced service delivery and emergency response | Increased land value, improved access to markets and social services, enhanced socio-economic inclusion | Proper road alignment planning, community involvement, phased upgrading and maintenance planning

## Cross_Cutting_Issues
No | Programme | Gender & Youth Inclusion | Climate & Environment | PWD Inclusion | Peace & Social Cohesion
1 | County Road Routine Maintenance Programme (Grading Works) | Engagement of women and youth through labour-based works and local employment opportunities | Improved drainage reduces erosion and road degradation during rains | Improved road access for PWDs to essential services | Improved mobility enhances interaction among communities and reduces isolation
2 | County Road Improvement Programme (Gravelling Works) | Youth and women prioritized for material hauling and routine works | Reduced dust and erosion through proper gravel surfacing and drainage | Safer and smoother road surfaces improve accessibility for PWDs | Enhanced connectivity supports economic interaction and social integration
3 | County Road Upgrading and Surfacing Programme (Bituminous/Tarmac Roads) | Employment opportunities for skilled and semi-skilled youth and women | Durable surfaces reduce maintenance-related environmental disturbance | Improved pedestrian safety and accessibility for PWDs in urban centres | Improved transport corridors enhance trade, interaction, and peaceful coexistence
4 | County Road Network Expansion Programme (New Road Openings) | Inclusive community participation in road identification and construction activities | Proper alignment planning minimizes environmental degradation | Improved access to services for PWDs in previously inaccessible areas | Enhanced access reduces marginalization and supports social inclusion
5 | County Road Drainage and Crossings Infrastructure Programme (Slabs, Drifts, Culverts) | Community involvement including women and youth in construction activities | Flood control structures reduce soil erosion and climate-related damage | Safer crossings improve mobility for PWDs | Reduced flood-related disruptions enhance safety and community resilience
6 | County Pedestrian Access and Footbridge Development Programme | Youth and women engaged in construction and maintenance activities | Climate-resilient designs reduce flood risks | Dedicated pedestrian infrastructure improves safety and access for PWDs | Safe crossings enhance interaction, school attendance, and community cohesion

## Challenges_Lessons
No | Programme | Key Challenges | Mitigation Measures | Lessons Learnt
1 | County Road Routine Maintenance Programme (Grading Works) | Frequent damage during rainy seasons; limited equipment availability Insecurity | Timely grading schedules, improved drainage, better equipment planning and sharing,Multi-Agency and Intergovernmental approach | Preventive maintenance is cheaper and more effective than reactive repairs,
2 | County Road Improvement Programme (Gravelling Works) | Scarcity of quality gravel materials; high maintenance demand Insecurity | Proper material sourcing, improved compaction, provision of adequate drainage,Multi-Agency and Intergovernmental approach | Quality materials and drainage significantly extend road lifespan
3 | County Road Upgrading and Surfacing Programme (Bituminous/Tarmac Roads) | High construction costs; land acquisition and utility conflicts,Road reserve encroachment | Phased implementation, early stakeholder engagement, proper design planning | Early planning and stakeholder involvement reduces delays and cost overruns
4 | County Road Network Expansion Programme (New Road Openings) | Community disputes over alignments; difficult terrain | Community consultations, participatory planning, technical surveys | Community ownership improves project acceptance and sustainability
5 | County Road Drainage and Crossings Infrastructure Programme (Slabs, Drifts, Culverts) | Flood damage and under-designed structures | Climate-resilient designs, proper hydraulic sizing, routine inspections | Climate-informed designs are critical in flood-prone areas