## Projects_Programmes
COUNTY GOVERNMENT OF MARSABIT
IMPLEMENTED PROJECTS AND PROGRAMMES DATA TEMPLATE
Department Name |  | Trdae,Tourism and Cooperative Development | [7 empty] | CERTIFICATION
Directorate / Unit |  | Trade,Tourism and Cooprative Development | [7 empty] | Prepared by | Designation | Signature | Date
CEC Member |  | Ledaany Jeremy
Chief Officer |  | Mahad Mohamed Dida
Reporting Officer |  | Hussein Kasa | [7 empty] | Approved by | Designation | Signature | Date
Reporting Period |  | 2013 - 2026
Date of Submission
No. | Project / Programme Name | Sub-County | Ward | Location / Site | Objective | Implementation Period (FY) | Budget Allocated (KES) | Funding Source (County/Partnership) | Status (Complete/ Incomplete/Not Started) | % Completion | Key Achievements / Outputs | Beneficiaries (No.) | Evidence Available (Photos/videos)
1 | Completion of Moyale Biashara street Market-Perimeter Fence, Water Tank, toilet and refuse bins | Moyale township | township | township |  | 2013/2014 | 7956606 | County | Complete
2 | Sololo Market-10 Stalls, Perimeter fencing, refuse bin and toilets | Sololo | Obbu | sololo town |  | 2013/2014 | 8292487 | County | Complete
3 | Butiye Open Air Market-Perimeter fencing ,Stalls and refuse bins | moyale | Butiye | Butiye |  | 2013/2014 | 7900728 | County | Complete
4 | Renovation of Office Blocks-Trade office | saku | central | mountain |  | 2013/2014 | 752164 | County | Complete
5 | Renovation of Co-operative office Block | saku | central | mountain |  | 2013/2014 | 406000 | County | Complete
6 | Turbi Market stalls | Turbi | Turbi | Turbi |  | 2014/2015 | 7061809 | County | Complete
7 | Maikona Market stalls | Maikona | Maikona | maikona |  | 2014/2015 | 6956299 | County | Complete
8 | Dukana Market Stalls | Dukana | dukana | dukana |  | 2014/2015 | 7802067 | County | Complete
9 | North/Horr Market-Completion | N/HORR | North horr | North Horr |  | 2014/2015 | 4997744 | County | Complete
10 | North/Horr Jua-Kali Sheds | N/HORR | North Horr | North Horr |  | 2014/2015 | 5450091 | County | Complete
11 | Sololo Jua-Kali Sheds | Sololo | Obbu | makutano |  | 2014/2015 | 4982480 | County | Complete
12 | Loiyangalani Market Stalls | Loiyangalani | loyangalani | loyangalani |  | 2014/2015 | 7679351 | County | Complete
13 | Kargi Market Stalls | Kargi | kargi | Kargi |  | 2014/2015 | 7582862 | County | Complete
14 | Korr Jua-Kali Sheds | Korr | Korr | Korr |  | 2014/2015 | 5410000 | County | Complete
15 | Laisamis Market-Completion | Laisamis | Laisamis | Laisamis |  | 2014/2015 | 4997774 | County | Complete
16 | Log-Logo Market Stalls | Log-Logo | Log-Logo | Loglogo |  | 2014/2015 | 6950372 | County | Not Complete
17 | Stores at Trade department headquarters | Marsabit Town | central | mountain |  | 2014/2015 | 1197585 | County | Complete
18 | Marsabit Temporary stalls | Marsabit Town | central | mountain |  | 2015/2016 | 14198902 | County | Complete
19 | Marsabit Modern Market | saku | central | mountain |  | From 2015 | 459000000 | County | Flagship project
20 | [7 empty] | County | Complete
21 | Kamboe Market shed | laisamis | loglogo | kamboe |  | 2015/2016 | 799124 | County | Complete
22 | Ngurnit market shed | korr | korr | ngurnit |  | 2015/2016 | 1997564 | County | Complete
23 | County Enterprise Fund(CEF) | County wide | countywide | countywide |  | 2015/2016 | 30000000 | County | Disbursed
24 | Piping ,Water tank, electricity and works at Laisamis Market | Laisamis | Laisamis | Laisamis |  | 2015/2016 | 1890000 | County | Complete
25 | Works and partitioning of Marsabit Biashara Center | saku | mountain | mountain |  | 2015/2016 | 1141881 | County | Complete
26 | Refurbishment, fencing and toilets and refuse bin at Gurumesa Market | Moyale | township | Gurumesa |  | 2015/2016 | 4999897 | County | Complete
27 | Toilet &Water tank-Kargi market | Laisamis | kargi south Horr | Kargi |  | 2016/2017 | 2000000 | County | Complete
28 | Completion, Fencing, Toilet& Water tank-log-logo market | Laisamis | Loglogo | loglogo |  | 2016/2017 | 3500000 | County | Complete
28 | Fencing, Toilet and water tank-Loiyangalani market | Loiyangalani | Loyangalani | Loyangalani |  | 2016/2017 | 2500000 | County | Complete
30 | Fencing, Toilet and water tank-Maikona market | North Horr | Maikona | Maikona |  | 2016/2017 | 2500000 | County | Complete
31 | Fencing, Toilet and water tank –Turbi Market | Turbi | Turbi | Turbi |  | 2016/2017 | 2500000 | County | Complete
32 | Fencing, Toilets and water tank-Dukana Market | North Horr | Dukana | Dukana |  | 2016/2017 | 2500000 | County | Complete
33 | Toilet and Water tank at sololo market | Moyale | sololo | sololo |  | 2016/2017 | 2500000 | County | Complete
34 | Vegetable Market at Ngurnit | lAisamis | korr | ngurnit |  | 2016/2017 | 2000000 | County | Complete
35 | Solar Panels at Kargi Market | Laisamis | kargi | kargi |  | 2017/2018 | 500000 | County | complete
36 | Electric Wiring at Laisamis Market | Laisamis | Laisamis | Laisamis |  | 2017/2018 | 500000 | County | Complete
37 | Completion of Log-Logo Market | Laisamis | loglogo | loglogo |  | 2017/2018 | 500000 | County | Complete
38 | Deep Freezer at Loiyangalani fisheries | Loiyangalani | loyangalani | loyangalani |  | 2017/2018 | 1200000 | County | Complete
39 | Solar Panels at Loiyangalani Market | Loiyangalani | loyangalani | loyangalani |  | 2017/2018 | 500000 | County | Complete
40 | Equiping of Sololo Makutano jua-kali sheds | moyale | sololo | mkutano |  | 2017/2018 | 1200000 | County | Complete
41 | Market Stalls at Sololo Town | moyale | sololo | sololo |  | 2017/2018 | 4000000 | County | Complete
42 | Market stalls at Waldaa | moyale | uran | walda |  | 2017/2018 | 3000000 | County | Complete
43 | Solar Panels at Dukana Market | Dukana | dukana | dukana |  | 2017/2018 | 500000 | County | Complete
44 | Toilets at Maikona Market | Maikona | maikona | maikona |  | 2017/2018 | 500000 | County | Complete
45 | Solar at Maikona Market | Maikona | Maikona | maikona |  | 2017/2018 | 600000 | County | Complete
46 | Equiping of North-Horr Jua-Kali sheds | N/Horr | North horr | North Horr |  | 2017/2018 | 3000000 | County | Complete
47 | Market Stalls at Obbu | Moyale | Obbu |  |  | 2018/2019 | 3000000 | County | Complete
48 | Boda Boda Shade at Obbu | Moyale | Obbu |  |  | 2018/2019 | 500000 | County | Complete
49 | Car Washing Machines at Butiye | moyale | Butiye | Butiye |  | 2018/2019 | 400000 | County | Complete
50 | Market stalls at Telesgay | Illeret | Illeret | Telesgay |  | 20182019 | 3000000 | County | Complete
51 | Fencing of Mt Marsabit Dairy | Laisamis | loglogo | loglogo |  | 2021/2022 | 1000000 | County | Complete
52 | Construction of County Industrial Park and Aggregation Center | Moyale | Golbo | odda-Qalaliwe |  | 2023/2034 | 50000000 | County | On-going
53 | Purchase of mineral detecting machine-Haldayan mineral mining cooperative society | Laisamis | Karare | Karare |  | 2023/2024 | 1100000 | County
54 | Renovation of Biashara center | Saku | central | mountain |  | 2023/2024 | 600000 | County
55 | Trade fair and exibition | saku | central | mountain |  | 2023/2024 | 2000000 | county
56 | trade fair and exibition | saku | central | mountain |  | 2024/2025 | 3000000 | County
OTHERS
57 | Department of trade,Tourism and Cooperative Development | Saku | central | mountain |  | 2023/2024 |  | LMS
strategic plan 2023-2027
58 | Marsabit Charpter Chamber of Commerce and Industrystrategic plan | Saku | central | mountain |  | 2022-2023
for 2022-2025
59 | Economic stimulus program market at Sessi | Moyale | central | Sessi |  | 2024/2025 |  | State department of Urban and Housing
60 | Coopoerative registration and Governace
61 | Leased Bongole Resort was leased to Jambo Travellers a Private Entity to run the facility | Saku | central |  |  | 2023/2024
62 | Marsabit county public private partnership policy was developed | Saku | central | mountain |  | 2024-2025 |  | Mercy Corps,USAID KUZA
63 | Capacity Building | [6 empty] | WFP,LMS,USAID NAWIRI,KUZA,CRDD

## key challenges,mitig.&lesson
No | Project / Programme | Key Challenges | Mitigation Measures | Lessons Learnt
1 | Markets | Congestion and poor waste management | Enforce stall allocation, improve waste collection | Proper management is critical for functionality
2 | Jua Kali Shades | Inadequate space and maintenance | Expand shades and establish maintenance plan | Artisans need organized and well-kept workspaces
3 | Solars | Vandalism and maintenance costs | Community security and routine servicing | Community ownership improves sustainability
4 | Boda Boda Shades | Disorder and conflicts among riders | Form rider associations and enforce rules | Organization improves service delivery
5 | Fencing | Damage and illegal entry | Regular inspection and repairs | Security infrastructure needs continuous upkeep
6 | Renovation Works | Delays and cost overruns | Better planning and supervision | Proper project planning prevents delays
7 | Piping Water and Electricity Connections | Leakages and power interruptions | Routine maintenance and monitoring | Reliable utilities boost business operations
8 | Temporary Stalls | Overcrowding and instability | Improve stall design and rotation system | Temporary structures still need standards
9 | Toilets and Water Tanks | Poor maintenance and cleanliness | Establish cleaning schedules and user fees | Sanitation facilities require consistent management

## Cross_Cutting_Issues
No | Project / Programme | Gender & Youth Inclusion | Climate & Environment | PWD Inclusion | Peace & Social Cohesion
1 | modern market | safety and security(lighting,fire assembly ) | Climate Resilience/adopting to change-should withstand stand | Wheel chair accesssible stalls | conlict sensitive neutral ground,inclusive allocation
2 |  | universal hygiene(Well maintained t,child care facilities for women traders | specific climate risk,eg storm water management,rain water harvesting system | Standard Desable toilets | (the fairness factor)
3 |  | Economic inclusion and affirmative action(setting aside 30 %construction contarct to women and youth | Climate Resilience/adopting to change-should withstand stand | sinks ,soap dispensors and hand dryers should be reachable | Design for social mixing-Lay out which allow people to interact
4 |  |  | waste management-organic waste to recycling
5 |  |  | Ecosystem and Biodiversity protection-eg greening using native plant
6

## Impact_Outcomes
No. | Project / Programme | Observed Impact on Community | Social / Economic Benefits | Sustainability Measures
1 | Markets | Improved organization of trade and reduced roadside vending | Increased trader incomes, job creation, and improved local economy | Market management system, user fees for maintenance, waste management
2 | Jua Kali Shades | Better working environment for artisans and reduced exposure to harsh weather | Increased productivity, skills development, and employment opportunities | Routine repairs, artisan association management, use of durable materials
3 | Solars | Improved access to reliable and clean energy | Reduced energy costs, enhanced business operations, and improved security | Regular maintenance, community ownership, and technical training
4 | Boda Boda Shades | Improved safety and organization of riders | Increased earnings, reduced conflicts, and improved service delivery | Shade maintenance plan, rider association oversight
| Fencing | Enhanced security of the market and reduced theft | Protection of assets, improved trader confidence, and reduced losses | Routine inspection and repairs, community policing
| Renovation Works | Improved market infrastructure and usability | Better business environment and increased customer attraction | Scheduled maintenance and budget allocation for repairs
| Piping Water and Electricity Connections | Improved access to essential utilities | Better business operations, improved hygiene, and reduced operational costs | Utility management plan and regular servicing
| Temporary Stalls | Increased trading space for small-scale traders | Increased livelihoods, especially for youth and women | Rotational allocation and maintenance by users
| Toilets and Water Tanks | Improved sanitation and hygiene in the market | Reduced health risks and better customer experience | Regular cleaning schedule and water management system