## Projects_Programmes
COUNTY GOVERNMENT OF MARSABIT
IMPLEMENTED PROJECTS AND PROGRAMMES DATA TEMPLATE
Department Name |  | Water,Enviroment and Natural Resources | [7 empty] | CERTIFICATION
Directorate / Unit |  | Water Services | [7 empty] | Prepared by | Designation | Signature | Date
CEC Member |  | Grace Galmo Boru | [7 empty] | Umuro Sharamo | Director,Water Services |  | 10.2.2026
Chief Officer |  | Boru Dulacha
Reporting Officer |  | Umuro Sharamo | [7 empty] | Approved by | Designation | Signature | Date
Reporting Period |  | 2013 - 2026 | [7 empty] | Boru Dulacha | Chief Officer,Water Services |  | 10.2.2026
Date of Submission
No. | Project / Programme Name | Sub-County | Ward | Location / Site | Objective | Implementation Period (FY) | Budget Allocated (KES) | Funding Source (County/Partnership) | Status (Complete/ Incomplete/Not Started) | % Completion | Key Achievements / Outputs | Beneficiaries (No.) | Evidence Available (Photos/videos)
1 | Bakuli IV Water & Sewerage Project | Marsabit |  | Saku | Water & sewer infrastructure |  | 1600000000 | County Government | Complete | 90
2 | Qolbot Dam |  | Golbo | Golbo | Dam construction | 2015/2016 | 30000000 | County Government | Complete | 100 | 86 boreholes drilled and equipped |  | Yes
3 | Badan Rero Dam |  | Obbu | Obbu | Dam construction | 2015/2016 | 30000000 | County Government | Complete | 98 | 97 boreholes rehabilitated and operationalized |  | Yes
4 | Kshwein Dam | Laisamis |  | Korr | Dam construction | 2015/2016 | 30000000 | County Government | Complete | 100 | 173 solarized |  | Yes
5 | Karare Dam | Marsabit | Karare | Karare | Dam construction | 2015/2016 | 35000000 | County Government | Complete | 100 | 80 installed with motors and pumps |  | Yes
6 | Sesala Dam | North Horr | Maikona | Maikona | Dam construction | 2015/2016 | 35000000 | County Government |  |  |  |  | yes
7 | Sololo Flood Mitigation Project | Sololo |  | Sololo | Flood mitigation |  | 50000000 | County Government |  |  |  |  | yes
8 | Qangam Medium Size Dam |  | Golbo | Golbo | Dam construction | 2025/2026 | 15000000 | County Government |  |  |  |  | yes
9 | Desilting & expansion Ongeli Pan | Laisamis | Korr | Ongeli | Earth pan works | 2017/2018 | 5000000 | County Government
10 | Hara Bargasa Pan Construction |  |  | Heelu | Earth pan construction | 2017/2018 | 7500000 | County Government
11 | Expansion Walda Dam |  | Golbo | Golbo | Earth pan expansion |  | 4000000 | County Government
12 | Desilting Marsabit Dam | Marsabit |  | Heelu | Desilting |  | 3000000 | County Government
13 | Desilting Bori Jadesa |  | Obbu | Obbu | Desilting |  | 2500000 | County Government
14 | Desilting Mukh Gurra |  | Obbu | Obbu | Desilting |  | 2500000 | County Government
15 | Drilling Borehole Iftin Uran | North Horr |  | Iftin/Uran | Borehole drilling | 2019/2020 | 5000000 | County Government
16 | Equipping Borehole |  |  |  | Borehole equipping | 2019/2020 | 4000000 | County Government
17 | Drilling & Equipping Malabraa Borehole |  |  | Malabraa | Borehole drilling/equipping | 2019/2020 | 4000000 | County Government
18 | Drilling & Equipping Nana Borehole |  |  | Nana | Borehole drilling/equipping | 2019/2020 | 6000000 | County Government
19 | Drilling & Equipping Kitur Borehole | North Horr | Maikona | Maikona | Borehole drilling/equipping | 2019/2020 | 5000000 | County Government
20 | Equipping El-Angburke Borehole | North Horr | Illeret | Illeret | Borehole equipping | 2019/2020 | 7350000 | County Government
21 | Drilling & Equipping Sakaridalla Borehole | Laisamis |  | Laisamis | Borehole drilling/equipping | 2018/2019 | 9200000 | County Government
22 | Drilling Manyatta Borehole | Laisamis |  | Laisamis | Borehole drilling | 2018/2019 | 5000000 | County Government
23 | Drilling & Equipping Gulcan Borehole | Laisamis | Merille | Merille | Borehole drilling/equipping | 2018/2019 | 8200000 | County Government
24 | Drilling & Equipping Golbo Borehole |  | Golbo | Golbo | Borehole drilling/equipping | 2018/2019 | 11700000 | County Government | Complete | 100 | 147 water pans constructed |  | Yes
25 | Drilling & Equipping Korr Borehole | Laisamis | Korr | Korr | Borehole drilling/equipping | 2018/2019 | 9000000 | County Government | Complete | 100 | 26 medium sized dams constructed and operationalized |  | Yes
26 | Loglogo Lesteng Water Pipeline | Laisamis |  | Loglogo/Lesteng | Pipeline extension | 2017/2018 | 5400000 | County Government | Complete | 100 | 32 rock catchment dams constructed |  | Yes
27 | Piping Sessi Township | Moyale |  | Sessi Township | Water pipeline |  | 2000000 | County Government | Ongoing | 85 | Bakuli IV Dam completed |  | Yes
28 | Piping Malbe Baal | Sololo | Obbu | Malbe/Baal | Water pipeline |  | 4000000 | County Government |  |  |  |  | yes
29 | Expansion Dukana Water Supply | North Horr |  | Dukana | Water supply expansion |  | 5000000 | County Government |  |  |  |  | yes
30 | Kalacha Water Supply Pipeline Expansion | North Horr |  | Kalacha | Pipeline expansion | 2017/2018 | 7000000 | County Government |  |  |  |  | yes
31 | North Horr Water Supply Expansion | North Horr |  | North Horr | Pipeline expansion | 2017/2018 | 9000000 | County Government |  |  |  |  | yes
32 | Kubi Galla Water Pipeline |  |  | Kubi Galla | Water pipeline | 2017/2018 | 15000000 | County Government |  |  |  |  | yes
33 | Solar Genset & Steel Tank Installation Karare | Marsabit | Karare | Karare | Water infrastructure |  | 10000000 | County Government |  |  |  |  | yes
34 | Expansion of Walda Dam – – Golbo – 200m³ | Sololo | Uran | Walda | Earth Pan Works (Desilting/Expansion/Construction) |  | 4000000 | County Govt |  |  |  |  | yes
35 | Desilting Marsabit Dam – – Heelu | Marsabit |  | Heelu | Earth Pan Works (Desilting/Expansion/Construction) |  | 3000000 | County Govt |  |  |  |  | yes
36 | Qolbot Dam – FY 2015–2016 – 30M (Golbo Ward) | Moyale | Golbo |  | Major Dams | 2015/2016 | 30000000
37 | Badan Rero Dam – FY 2015–2016 – 30M (Obbu Ward) | Sololo | Obbu | Badan Rero | Major Dams | 2015/2016 | 30000000
38 | Kshwein Dam – FY 2015–2016 – 30M (Korr) |  |  |  | Major Dams | 2015/2016 | 30000000
39 | Karare Dam – FY 2015–2016 – 35M (Karare Ward) |  |  |  | Major Dams | 2015/2016 | 35000000
40 | Sesala Dam – FY 2015–2016 – 35M (Maikona Ward) |  |  |  | Major Dams | 2015/2016 | 35000000
41 | Qangam Medium Size Dam (Golbo) – FY 2025/2026 – 15M |  |  |  | Major Dams | 2025/2026 | 15000000
42 | Expansion of Walda Dam – 4M – Golbo – 200m³ | Sololo | Uran | Walda | Earth Pans |  | 4000000
43 | Desilting Marsabit Dam – 3M – Heelu | Saku |  |  | Earth Pans |  | 3000000
44 | Dambala Fachana – Borehole – Obbu – Cost: 3M | Sololo | Obbu | Dambala Fachana | Borehole List (Location / Cost / FY) |  | 3000000
45 | Konon Gos Water Pan | North horr | Konon Gos Village | Konon Gos Village | Provide water availability and access for households and institutions | 2022-2026 |  | World Bank-Water Sector Trust Fund | Complete | 100 |  |  | Yes
46 | Desilting & Expansion – Ongeli Pan – Cost: – – Korr Ward | Laisamis |  | Korr Ward | Earth Pan Works (Desilting/Expansion/Construction) | FY 2017/2018 | 5000000 | County Govt |  |  |  |  | yes
47 | Desilting & Expansion – Ongeli Pan – Cost: 5M – FY 2017/2018 – Korr Ward |  |  |  | Earth Pans | 2017/2018 | 5000000
48 | OTHER
49 | Construction of underground tanks | Laisamis,North Horr | North Horr,Dukana,Maikona,Turbi-Bubisa,Korr/Ngurunit | Laisamis and North Horr Subcounties | Provide water avaiability and access for households and institutions | 2013-2026 | 352000000 | County Government of Marsabit and partners | Complete | 100 | 88 underground tanks constructed |  | Yes
50 | Construction of masonry tanks | Saku Laisamis,Moyale,North Horr | Sagante/Jaldesa,Karare,,Korr/Ngurunit,Kargi/South Horr,North Horr,Illeret,Dukana,Maikona,Turbi/Bubisa,Uran,Sololo,Golbo,Butiye,0bb | Sagante/Jaldesa,Karare,,Korr/Ngurunit,Kargi/South Horr,North Horr,Illeret,Dukana,Maikona,Turbi/Bubisa,Uran,Sololo,Golbo,Butiye,0bb | Provide water avaiability and access for households and institutions | 2013-2026 | 30400000 | County Government of Marsabit and partners | Complete | 100 | 76 masonry tanks constructed |  | Yes
51 | Repair and rehabilitatio of shallow wells | Saku,Laisamis,North Horr | Sagante/Jaldesa,Laisamis,Dukana,Maikona,North Horr | Sagante/Jaldesa,Laisamis,Dukana,Maikona,North Horr | Provide water availability and access for households and institutions | 2013-2026 | 11000000 | County Government of Marsabit and partners | Complete | 100 | 44 shallow wells rehabilitated and protected |  | Yes
52 | Purchase and distribution of rains water harvesting plastic tanks | Saku,Moyale,North Horr,Laisamis | Sagante/Jaldesa,Karare,,Korr/Ngurunit,Kargi/South Horr,North Horr,Illeret,Dukana,Maikona,Turbi/Bubisa,Uran,Sololo,Golbo,Butiye,0bb | Sagante/Jaldesa,Karare,,Korr/Ngurunit,Kargi/South Horr,North Horr,Illeret,Dukana,Maikona,Turbi/Bubisa,Uran,Sololo,Golbo,Butiye,0bb | Provide water availability and access for households and institutions | 2013-2026 | 356000000 | County Government of Marsabit and partners | Complete | 100 | 4450 plastic water tanks purchased and distributed |  | Yes
53 | Innovation and technology support | Saku,Moyale,North Horr,Laisamis | Sagante/Jaldesa,Karare,,Korr/Ngurunit,Kargi/South Horr,North Horr,Illeret,Dukana,Maikona,Turbi/Bubisa,Uran,Sololo,Golbo,Butiye,0bb | Sagante/Jaldesa,Karare,,Korr/Ngurunit,Kargi/South Horr,North Horr,Illeret,Dukana,Maikona,Turbi/Bubisa,Uran,Sololo,Golbo,Butiye,0bb | Strengthen water governance | 2013-2026 | 112,00,000 | County Government of Marsabit and partners | Complete | 100 | 112 water kiosks automated |  | Yes
54 | Horn of Africa Groundwater for Resilience ;Project | Saku,Moyale,North Horr,Laisamis | Sagante/Jaldesa,Loglogo,Laisamis,Korr/Ngurunit,North Horr,Illeret,Dukana,Maikona,Sololo | Sagante/Jaldesa,Loglogo,Laisamis,Korr/Ngurunit,North Horr,Illeret,Dukana,Maikona,Sololo | Improve and strengthen rural water availabilitya and access | 2024-2026 | 800000000 | World Bank-Water Sector Trust Fund | Ongoing | 7 | Site handing over to contractors done |  | Yes
55 | SWASAP II | Moyale, Laisamis,North Horr | Korr,Dukana, Obbu and Dabel | Farakoren, Dukana Borehole, Sololo Ramata and Dabel | Provide water availability and access for households and institutions | 2025-2026 | 100000000 | Danida(Kenya Redcross) | Just Started | >10% | Improved access to water both human and Livestock |  | yes
56 | Bakuli IV Project – GoK / ADB | Marsabit |  | Water & Sewerage – SACCI | Dam / Water Storage Infrastructure |  | 1600000000 | GoK / ADB |  |  |  |  | yes
57 | Sololo Town Flood Mitigation Project | Sololo |  | 50M | Dam / Water Storage Infrastructure |  | 50000000 | County Govt |  |  |  |  | yes
58 | Construction of Hara Bargasa – – – Heelu |  |  | Heelu | Earth Pan Works (Desilting/Expansion/Construction) | FY 2017/2018 | 7500000 | County Govt |  |  |  |  | yes
59 | Desilting Bori Jadesa – – Obbu |  |  | Obbu | Earth Pan Works (Desilting/Expansion/Construction) |  | 2500000 | County Govt |  |  |  |  | yes
60 | Desilting Mukh Gurra – – Obbu |  |  | Obbu | Earth Pan Works (Desilting/Expansion/Construction) |  | 2500000 | County Govt |  |  |  |  | yes
61 | Drilling – Manyatta – – Laisamis | Laisamis |  | Laisamis | Borehole Drilling and/or Equipping |  | 5000000 | County Govt |  |  |  |  | yes
62 | Drilling & Equipping – Gulcan – – Merille / Laisamis Ward | Laisamis |  | Merille / Laisamis Ward | Borehole Drilling and/or Equipping |  | 8200000 | County Govt |  |  |  |  | yes
63 | Drilling & Equipping – Korr – – Korr Town | Laisamis |  | Korr Town | Borehole Drilling and/or Equipping |  | 9000000 | County Govt |  |  |  |  | yes
yes
64 | Bakuli IV Project – GoK / ADB – 1.6B (Water & Sewerage – SACCI) |  |  |  | Major Dams |  | 1600000000
65 | Sololo Town Flood Mitigation Project – 50M |  |  |  | Major Dams |  | 50000000
66 | Construction of Hara Bargasa – 7.5M – FY 2017/2018 – Heelu |  |  |  | Earth Pans |  | 7500000
67 | Desilting Bori Jadesa – 2.5M – Obbu |  |  |  | Earth Pans |  | 2500000
68 | Desilting Mukh Gurra – 2.5M – Obbu |  |  |  | Earth Pans |  | 2500000
69 | Drilling – Manyatta – 5M – Laisamis |  |  |  | Borehole Drilling & Equipping (FY 2018/2019) |  | 5000000
70 | Drilling & Equipping – Gulcan – 8.2M – Merille / Laisamis Ward |  |  |  | Borehole Drilling & Equipping (FY 2018/2019) |  | 8199999
71 | Drilling & Equipping – Korr – 9M – Korr Town |  |  |  | Borehole Drilling & Equipping (FY 2018/2019) |  | 9000000
72 | Drilling & Equipping – Nana – 6M |  |  |  | Borehole Projects (FY 2019/2020) |  | 6000000
73 | Loglogo Water – Lesteng – 4 km – Cost: 5.4M – FY 2017/2018 |  |  |  | Extension Pipelines |  | 5400000
74 | Equipping Solar, Genset & Steel Tank – Karare – 10M |  |  |  | Extension Pipelines |  | 10000000
75 | Yell – High yield – Karare – Cost: 5M – FY 2017/2018 |  |  |  | Borehole List (Location / Cost / FY) |  | 5000000
76 | Ongeli – Low yield – Korr – Cost: 5M – FY 2017/2018 |  |  |  | Borehole List (Location / Cost / FY) |  | 5000000
77 | Balaah – Low yield – Korr – Cost: 5M – FY 2017/2018 |  |  |  | Borehole List (Location / Cost / FY) |  | 5000000
78 | Gullheilan – Low yield – Korr – Cost: 4M – FY 2017/2018 |  |  |  | Borehole List (Location / Cost / FY) |  | 4000000
79 | Serari – Medium – Korr – Cost: 5M – FY 2017/2018 |  |  |  | Borehole List (Location / Cost / FY) |  | 5000000
80 | Drilling & Equipping – Godolo – Uran (Golde) – Cost: 5M |  |  |  | Borehole List (Location / Cost / FY) |  | 5000000
81 | Drilling – Liban Fadjo – Uran – Cost: 5M |  |  |  | Borehole List (Location / Cost / FY) |  | 5000000
82 | Drilling & Equipping – Funan Qumbi – Cost: 5M |  |  |  | Borehole List (Location / Cost / FY) |  | 5000000
83 | Pipelines extensiton to settlments and public institutions | Saku,Moyale,North Horr,Laisamis | Sagante/Jaldesa,Karare,,Korr/Ngurunit,Kargi/South Horr,North Horr,Illeret,Dukana,Maikona,Turbi/Bubisa,Uran,Sololo,Golbo,Butiye,0bb | Sagante/Jaldesa,Karare,,Korr/Ngurunit,Kargi/South Horr,North Horr,Illeret,Dukana,Maikona,Turbi/Bubisa,Uran,Sololo,Golbo,Butiye,0bb | Reduce household return trekking distances to water sources | 2013-2026 | 430000000 | County Government of Marsabit and partners | Complete | 98 | 860km of pipeline extension to settlements and institutions done |  | Yes
84 | Elmoyo Water Supply | Loiyangalani | Layeni and Komothe | Layeni and Komothe | Purification of lake water for household use | 2022-2024 | 50000000 | World Bank-Water Sector Trust Fund | Complete | 100
85 | North Horr Water SupplyNorth Horr |  | North Horr Trading Centre | North Horr Trading Centre | Provide water availability and access for households and institutions | 2022-2025 |  | World Bank-Water Sector Trust Fund | Complete | 100 |  |  | Yes
86 | Oltorot Water Supply |  | Oltorot Trading Centre | Oltorot Trading Centre | Provide water availability and access for households and institutions | 2022-202 |  | World Bank-Water Sector Trust Fund | Complete | 100 |  |  | Yes
87 | Barambate Water Supply |  | North Horr |  | Provide water availability and access for households and institutions |  |  | World Vision Kenya | Complete | 100 |  |  | Yes
88 | Piping – Sessi Township – Moyale – 2M | Moyale | Township | Sessi Township | Extension Pipelines |  | 2000000
89 | Piping – Malbe – Baal – Obbu – 4M – 5 km | Sololo | Obbu | Malbe/Baal | Extension Pipelines |  | 4000000
90 | Expansion – Dukana Water Supply | Sololo | Uran | Dukana | Extension Pipelines |  | 5000000
91 | Kalacha Water Supply Expansion of Pipelines | North Horr | kalacha | kalacha | Extension Pipelines | FY 2017/2018 | 7000000
92 | Expansion – North Horr Water Supply | North Horr | North Horr | North Horr | Extension Pipelines | FY 2017/2018 | 9000000
93 | Piping of Water – Kubi Galla – Gadgallo / Harlake |  |  |  | Extension Pipelines | FY 2017/2018 | 15000000

## Impact_Outcomes
No. | Project / Programme | Observed Impact on Community | Social / Economic Benefits | Sustainability Measures
1 | Borehole Drilling | Improve access to clean water | Improved revenue collection, an alternative livelihood | Trained Management committee/ intending to form Rural Water Supply Company
2 | Construction Waterpans | Improve access to water for livestock | utilised for irrigation,surface runoff harvesting | Capacity building of users,regular desilting
3 | Expansion of pipelines | individual connections and improved access to clean water | improved livelihood, income generating | Regular repair and maintenance, strict tarriff payments
4 | Installation of Prepaid Meters | Provide employment, No loss of water, no theft of revenue, livelihood improved | Sustainable revenue collections, improved income per capita. | Regular maintenance, upgrading when required
5 | Procure of UPVC tanks | Availble water at the households | Clean and safe water for drinking | Regular Maintenance of channels and gutters

## Challenges_Lessons
No | Project / Programme | Key Challenges | Mitigation Measures | Lessons Learnt
1 | Drilling of New boreholes | Drilled dry | Must establish rich aquifer using modern survey technics | Good Management
2 | Construction of Dams and earthpans | Silt, Evaporation and Not Clean | Silt traps, regular desilting | Rainwater harveseting,
3 | Construction of pipelines | Leakages, Vandalism | regular line patrols | Maintein quality standard
4 | Prepaid meters | High installation cost , new tecnology | Regular upgrade | No loss of water or revenue, efficient
5

## Cross_Cutting_Issues
No | Project / Programme | Gender & Youth Inclusion | Climate & Environment | PWD Inclusion | Peace & Social Cohesion
1
2
3
4
5
6